## Implementation Plan
ID | Task | Description | Type | Priority | Status | Owner | Start Date | End Date | Actual Date | Completion % | Pre-requisite / Dependencies | Risk | Proposed Mitigation | Deliverables | YAS Sign-off Owner | Comments
1 | Discovery & Planning
1.1 | Project Kick-off | Establish Steering Committee, RACI matrix, communication plan, and project cadence. | Milestone | High | To Do | Novac & Santam Team | TBD | TBD |  | 0%
1.2 | Functional Discovery: Core Products | Workshops to define Leisure, Corporate, and Inbound travel insurance product rules, limits, and rating tables. | Task | Critical | To Do | Novac Product Team | TBD | TBD |  | 0% | [5 empty] | Multi-currency focus
1.3 | Functional Discovery: Workflow & UI | Wireframing B2B portal, call centre screens, underwriting escalation, and automated renewal triggers. | Task | High | To Do | Novac Product Team | TBD | TBD |  | 0%
1.4 | Functional Discovery: Claims & Finance | Map claims triage, STP rules, reserve calculations, GL mapping, and multi-insurer bordereaux logic. | Task | Critical | To Do | Novac Product Team | TBD | TBD |  | 0% |  | Complex GL structures | Early Santam Finance engagement
1.5 | Technical Discovery: Enterprise Integrations | Document API specs for D365 CRM, Telephony (CTI), Enterprise DMS, Central Payment Gateway, and Snowflake. | Task | Critical | To Do | Novac Dev Team | TBD | TBD |  | 0%
1.6 | Infrastructure & Security Architecture | Finalize AWS landing zone, VPC design, WAF rules, IAM roles, encryption (AES-256), and DR strategy. | Task | High | To Do | Novac Dev Team | TBD | TBD |  | 0% |  | Infosec policy clashes | Pre-align with Sanlam InfoSec
1.7 | Phase 1 Sign-off Gate | Formal business and technical sign-off of Fit-Gap analysis and technical blueprints. | Milestone | Critical | To Do | Novac & Santam Team | TBD | TBD |  | 0% |  |  |  | Fit-Gap analysis and technical blueprints.
2 | Implementation
2.1 | Dev & QA Environment Provisioning | Setup servers, and CI/CD pipelines for Dev and QA environments. | Task | High | To Do | Novac Dev Team | TBD | TBD |  | 0%
2.2 | Rating Engine & Product Setup | Configure base rates, age-band multipliers, pre-existing condition loadings, and multi-currency exchange feeds. | Task | Critical | To Do | Novac Dev Team | TBD | TBD |  | 0%
2.3 | Document & Communication Engine | Build templates for Policy Schedules, Visa Letters, Claims Reject/Accept letters. Configure SMS/Email triggers. | Task | Medium | To Do | Novac Dev Team | TBD | TBD |  | 0%
2.4 | B2B Partner & Call Centre Portal | Build Annexure B requirements: multi-tier broker hierarchies, commission splits, and quote-to-bind flows. | Task | High | To Do | Novac Dev Team | TBD | TBD |  | 0%
2.5 | Core PAS Sprint Demo & Acceptance | End-to-end demonstration of offline policy lifecycle (Quote, Bind, Endorse, Cancel, Claim). | Milestone | High | To Do | Novac Dev Team | TBD | TBD |  | 0% | [5 empty] | Pre-integration
2.6 | D365 CRM Integration (Bi-directional) | Build APIs to sync customer profiles, interaction logs, and policy status updates to Dynamics 365. | Task | Critical | To Do | Novac & Santam Team | TBD | TBD |  | 0% | D365 Sandbox
2.7 | Finance Integration (GL & Bordereaux) | Develop daily batch extracts for GL, accounts payable/receivable, and Reinsurance/Multi-insurer splits. | Task | Critical | To Do | Novac Dev Team | TBD | TBD |  | 0%
2.8 | Payment Gateway (Premium & Refunds) | Integrate with Santam Central Gateway for tokenized credit card auth, EFT tracking, and automated refund pushing. | Task | High | To Do | Novac Dev Team | TBD | TBD |  | 0% | Gateway keys
2.9 | Enterprise DMS Integration | Develop API push mechanism to store generated PDF schedules/claims docs into Santam central repository. | Task | Medium | To Do | Novac Dev Team | TBD | TBD |  | 0%
2.10 | Data Warehouse / Snowflake Integration | Configure CDC (Change Data Capture) feeds from STATIM RDS to Santam Snowflake for reporting. | Task | High | To Do | Novac Dev Team | TBD | TBD |  | 0%
2.11 | Code Freeze & Integration Review | Freeze development environment. Code review and static application security testing (SAST). | Milestone | High | To Do | Novac Dev Team | TBD | TBD |  | 0%
3 | Data Migration
3.1 | Legacy Data Profiling, Mapping & Clean-up | Analyze SystemaTIC database schema, map fields to STATIM, identify and perform data cleansing requirements. | Task | High | To Do | Santam Team | TBD | TBD |  | 0% |  | Poor data quality | Santam executes pre-migration clean | Mapping Doc
3.2 | Prod Data Extract | Client to provide production data extract | Task | Critical | To Do | Santam Team | TBD | TBD |  | 0%
3.3 | ETL Script Development | Write extraction, transformation, and load scripts for active policies, historical claims, and broker networks. | Task | Critical | To Do | Novac Migration Team | TBD | TBD |  | 0% | Prod Data Extract | Logic failures | Peer review ETL scripts
3.4 | Mock Migration 1 | Execute initial full data load into Dev. Validate record counts, financial balances, and referential integrity. | Task | Critical | To Do | Novac Migration Team | TBD | TBD |  | 0% |  | High error fallout | Tune ETL scripts iteratively
3.5 | Mock Migration 2 | Second pass migration using cleansed data for formal QA and UAT baseline data setup. | Task | High | To Do | Novac Migration Team | TBD | TBD |  | 0% |  | Extended execution time | Optimize indexing and bulk inserts |  |  | Sets stage for QA
3.6 | Mock 2 Validation | Business review of migrated data for accuracy | Task | Critical | To Do | Santam Team | TBD | TBD |  | 0%
3.7 | Data Migration Sign-off | Client to provide sign-off for the migrated data | Milestone | Critical | To Do | Santam Team | TBD | TBD |  | 0%
4 | Quality Assurance
4.1 | SIT Test Case Preparation |  | Task | High | To Do | Novac QA Team | TBD | TBD |  | 0%
4.2 | Product, Rules & workflows configuration - Specific for Regression execution |  | Task | High | To Do | Novac QA Team | TBD | TBD |  | 0%
4.3 | SIT Execution | End-to-end execution of test cases across core PAS, portals, and all enterprise integrations (D365, Payment, etc.). | Task | Critical | To Do | Novac QA | TBD | TBD |  | 0%
4.4 | SIT Bug Fixes | Fix defects arising from QA environment execution | Task | High | To Do | Novac QA Team | TBD | TBD |  | 0%
4.5 | SIT Bug Re-testing & Fixes | Verify fixes and re-open failures if necessary | Task | High | To Do | Novac QA Team | TBD | TBD |  | 0%
4.6 | SIT Closure | Conclude primary SIT phase | Task | High | To Do | Novac QA Team | TBD | TBD |  | 0%
4.7 | Regression Testing | Execute regression on impacted functionality | Task | High | To Do | Novac QA Team | TBD | TBD |  | 0%
4.8 | Regression Bug Fixes | Fix bugs identified during regression | Task | High | To Do | Novac QA Team | TBD | TBD |  | 0%
4.9 | Regression Bug Re-testing & Fixes | Validate regression fixes | Task | High | To Do | Novac QA Team | TBD | TBD |  | 0%
4.10 | Regression Closure | Conclude regression phase | Task | High | To Do | Novac QA Team | TBD | TBD |  | 0%
4.11 | Vulnerability & Penetration Testing (VAPT) | Third-party/Santam InfoSec executes dynamic application security testing (DAST) and network pen-testing. | Task | Critical | To Do | Novac & Santam Team | TBD | TBD |  | 0% |  |  |  | VAPT Report
4.12 | Performance & Load Testing | Simulate concurrent portal users and bulk batch processing (renewals/finance) to validate AWS auto-scaling. | Task | High | To Do | Novac Dev & QA Team | TBD | TBD |  | 0% |  |  |  | Performance Test Report
4.13 | QA Sign-off | Obtain formal QA sign-off confirming exit criteria met | Milestone | Critical | To Do | Novac QA Team | TBD | TBD |  | 0%
4.14 | Addressing Product Configuration gaps | Address any configuration gaps | Task | Medium | To Do | Novac Product Team | TBD | TBD |  | 0%
5 | User Acceptance Testing
5.1 | UAT Test Plan & Test Case Creation | Select critical UAT scenarios focusing on business processes | Task | High | To Do | Santam Team | TBD | TBD |  | 0%
5.2 | UAT Environment Refresh | Push Regression passed code and Mock 2 data to UAT | Task | High | To Do | Santam Team | TBD | TBD |  | 0%
5.3 | UAT - Train the trainers | Conduct deep-dive sessions on Product Configurator, Rules Engine, and User Access Management for Santam Admins. | Task | Medium | To Do | Novac & Santam Team | TBD | TBD |  | 0%
5.4 | User Acceptance Testing (UAT) Execution | Santam business users execute real-world scenarios, testing usability, accuracy, and operational readiness. | Task | Critical | To Do | Santam Team | TBD | TBD |  | 0% |  | UAT tester unavailability | Pre-book UAT calendar in Inception | UAT Defect Log
5.5 | UAT Change / Enhancement Request (If applicable) | Log any scope changes discovered during UAT | Task | Medium | To Do | Santam Team | TBD | TBD |  | 0%
5.6 | UAT Defect Resolution | Resolve blocker defects logged by Business Users | Task | High | To Do | Novac Dev Team | TBD | TBD |  | 0%
5.7 | UAT Defect Re-Testing & CR / Enhancement Testing | Validate UAT fixes and new CRs | Task | High | To Do | Novac & Santam Team | TBD | TBD |  | 0%
5.8 | UAT Sign-off | Formal review of outstanding defects (must be zero Sev 1/Sev 2) | Milestone | Critical | To Do | Santam Team | TBD | TBD |  | 0%
6 | Go-Live Readiness
6.1 | Production Environment Provisioning | Provision AWS EC2, RDS, S3, and setup CI/CD pipelines, configure production SSLs, IP whitelists, and production DR sync. | Task | Critical | To Do | Novac DevOps Team | TBD | TBD |  | 0% |  | Network routing blocks | Final run-through with Networks
6.2 | Cutover Planning & Runbook Finalization | Finalize minute-by-minute cutover sequence, communication plan, and fail-back strategy. | Task | High | To Do | Novac & Santam Team | TBD | TBD |  | 0% |  | Misaligned responsibilities | Walkthrough runbook with all teams
6.3 | Final Data Migration (Cutover Weekend) | Freeze SystemaTIC. Execute final Delta ETL load into STATIM Production. Reconcile final GL balances. | Task | Critical | To Do | Novac Migration Team | TBD | TBD |  | 0% |  | Delta load exceeds window | Pre-load historicals, only delta on weekend |  |  | Weekend Task
7 | Go-Live
7.1 | Go / No-Go Decision | Final authorization for production launch (Configurations & Data) | Task | Critical | To Do | Steering Committee | TBD | TBD |  | 0%
7.2 | Go-Live | Execute minimal impact live transactions to verify integrations. Switch DNS. Formally declare Go-Live. | Milestone | Critical | To Do | Novac & Santam Team | TBD | TBD |  | 0% |  | Smoke test failure | Execute rollback to SystemaTIC | Live System
8 | Post Go-Live
8.1 | Hypercare Support (L2 & L3) | Immediate triage and ongoing support | Task | Critical | To Do | Novac Support Team | TBD | TBD |  | 0% |  | High query volume | Santam L1 to heavily filter queries
8.2 | BAU Transition & Project Closure | Formal sign-off transitioning platform into standard Application Maintenance and Support (AMS) SLA. | Milestone | High | To Do | Novac & Santam Team | TBD | TBD |  | 0% |  | Unresolved minor defects | Migrate to BAU backlog

## Timeline
Phase / Month (Full Solution) | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7
Discovery & Planning
Implementation
Data Migration
Quality Assurance
User Acceptance Testing
Go-Live Readiness
Go-Live
Post Go-Live

## RACI
Phase | Activity | Novac Steering Committee | Novac PMO Team | Novac Product Team | Novac Dev Team | Novac QA Team | Santam Steering Committee | Santam PMO Team | Santam Product Team | Santam Business Owner | Santam IT/Data Admin
Discovery & Planning | Project Kick-off | I | R | C | I | I | A | R | C | I | I
| Functional Discovery | I | A | R | C | I | A | I | R | C | C
| Technical & Arch Discovery | I | A | C | R | I | I | I | I | I | A, C
| Phase 1 Sign-off Gate | I | A | I | I | I | A | R | C | C | C
Implementation | Environment Provisioning | I | A | I | R | I | I | I | I | I | C
| Core Platform Configuration | I | A | R | R | I | I | I | C | C | I
| Enterprise Integrations | I | A | C | R | I | I | I | I | I | A, C
| Code Freeze & Review | I | A | I | R | C | I | I | I | I | I
Data Migration | SystemaTIC Data Clean-up | I | I | I | I | I | I | I | C | A | R
| ETL Scripts Development | I | A | I | R | I | I | I | I | I | C
| Mock Migration Executions | I | A | I | R | C | I | I | I | I | C
| Migration Data Validation | I | A | C | I | C | I | I | R | A,R | C
Quality Assurance | SIT Execution | I | A | C | I | R | I | I | I | I | I
| Defect Fixing (SIT) | I | A | C | R | C | I | I | I | I | I
| VAPT (Security Testing) | I | I | I | C | I | I | I | I | I | A, R
| QA Sign-off | I | A | I | I | R | I | I | I | I | I
User Acceptance Testing | UAT Environment Setup | I | A | I | R | I | I | A | I | I | R
| UAT Test Case Creation | I | I | C | C | C | I | A | R | C | I
| UAT Execution | I | I | C | I | C | I | I | R | A, R | I
| UAT Defect Triage | I | A | C | C | R | I | I | R | A | I
| UAT Defect Resolution | I | A | C | R | R | I | I | C | C | C
| UAT Sign-off | I | I | I | I | I | A | R | C | A, R | I
Go-Live | Legacy System Freeze | I | I | I | I | I | A | I | I | I | R
| Final Prod Data Cutover | I | A | I | R | I | I | I | I | I | C
| Go / No-Go Decision | A,R | C | C | C | C | A,R | C | C | C | C
| Go-Live | I | A | C | R | C | I | I | C | C | R
Post Go-Live | Hypercare Support (L2 & L3) | I | A | C | R | C | I | I | C | C | C
| BAU Transition & Project Closure | A | R | R | I | I | A | R | C | R | C
Key
R = Responsible | C = Consulted
A = Accountable | I = Informed