## Implementation Plan
[7 empty] | ê | ê | ê
ID | Task | Description | Type | Priority | Status | Owner | Duration (Days) | Phase Duration (Weeks) | Critical Path | Start Date | End Date | Actual Date | Completion % | Pre-requisite / Dependencies | Risk | Proposed Mitigation | Deliverables | YAS Sign-off Owner | Comments
1 | Discovery & Planning | [6 empty] | 8 Weeks
1.1 | Project Kick-off | Establish Steering Committee, RACI matrix, communication plan, and project cadence. | Milestone | High | To Do | Novac & Santam Team | 1 |  | Yes | TBD | TBD |  | 0%
1.2 | Functional Discovery: Core Products | Workshops to define Leisure, Corporate, and Inbound travel insurance product rules, limits, and rating tables. | Task | Critical | To Do | Novac Product Team | 10 |  | Yes | TBD | TBD |  | 0% | [5 empty] | Multi-currency focus
1.3 | Functional Discovery: Workflow & UI | Wireframing B2B portal, call centre screens, underwriting escalation, and automated renewal triggers. | Task | High | To Do | Novac Product Team | 8 |  | No | TBD | TBD |  | 0%
1.4 | Functional Discovery: Claims & Finance | Map claims triage, STP rules, reserve calculations, GL mapping, and multi-insurer bordereaux logic. | Task | Critical | To Do | Novac Product Team | 8 |  | Yes | TBD | TBD |  | 0% |  | Complex GL structures | Early Santam Finance engagement
1.5 | Technical Discovery: Enterprise Integrations | Document API specs for D365 CRM, Telephony (CTI), Enterprise DMS, Central Payment Gateway, and Snowflake. | Task | Critical | To Do | Novac Dev Team | 8 |  | Yes | TBD | TBD |  | 0%
1.6 | Infrastructure & Security Architecture | Finalize AWS landing zone, VPC design, WAF rules, IAM roles, encryption (AES-256), and DR strategy. | Task | High | To Do | Novac Dev Team | 4 |  | No | TBD | TBD |  | 0% |  | Infosec policy clashes | Pre-align with Sanlam InfoSec
1.7 | Phase 1 Sign-off Gate | Formal business and technical sign-off of Fit-Gap analysis and technical blueprints. | Milestone | Critical | To Do | Novac & Santam Team | 1 |  | Yes | TBD | TBD |  | 0% |  |  |  | Fit-Gap analysis and technical blueprints.
2 | Implementation | [6 empty] | 12 Weeks
2.1 | Dev & QA Environment Provisioning | Setup servers, and CI/CD pipelines for Dev and QA environments. | Task | High | To Do | Novac Dev Team | 10 |  | Yes | TBD | TBD |  | 0%
2.2 | Rating Engine & Product Setup | Configure base rates, age-band multipliers, pre-existing condition loadings, and multi-currency exchange feeds. | Task | Critical | To Do | Novac Dev Team | 30 |  | Yes | TBD | TBD |  | 0%
2.3 | Document & Communication Engine | Build templates for Policy Schedules, Visa Letters, Claims Reject/Accept letters. Configure SMS/Email triggers. | Task | Medium | To Do | Novac Dev Team | 15 |  | No | TBD | TBD |  | 0%
2.4 | B2B Partner & Call Centre Portal | Build Annexure B requirements: multi-tier broker hierarchies, commission splits, and quote-to-bind flows. | Task | High | To Do | Novac Dev Team | 30 |  | Yes | TBD | TBD |  | 0%
2.5 | Core PAS Sprint Demo & Acceptance | End-to-end demonstration of offline policy lifecycle (Quote, Bind, Endorse, Cancel, Claim). | Milestone | High | To Do | Novac Dev Team | 2 |  | Yes | TBD | TBD |  | 0% | [5 empty] | Pre-integration
2.6 | D365 CRM Integration (Bi-directional) | Build APIs to sync customer profiles, interaction logs, and policy status updates to Dynamics 365. | Task | Critical | To Do | Novac & Santam Team | 20 |  | Yes | TBD | TBD |  | 0% | D365 Sandbox
2.7 | Finance Integration (GL & Bordereaux) | Develop daily batch extracts for GL, accounts payable/receivable, and Reinsurance/Multi-insurer splits. | Task | Critical | To Do | Novac Dev Team | 20 |  | Yes | TBD | TBD |  | 0%
2.8 | Payment Gateway (Premium & Refunds) | Integrate with Santam Central Gateway for tokenized credit card auth, EFT tracking, and automated refund pushing. | Task | High | To Do | Novac Dev Team | 15 |  | No | TBD | TBD |  | 0% | Gateway keys
2.9 | Enterprise DMS Integration | Develop API push mechanism to store generated PDF schedules/claims docs into Santam central repository. | Task | Medium | To Do | Novac Dev Team | 12 |  | No | TBD | TBD |  | 0%
2.10 | Data Warehouse / Snowflake Integration | Configure CDC (Change Data Capture) feeds from STATIM RDS to Santam Snowflake for reporting. | Task | High | To Do | Novac Dev Team | 12 |  | No | TBD | TBD |  | 0%
2.11 | Code Freeze & Integration Review | Freeze development environment. Code review and static application security testing (SAST). | Milestone | High | To Do | Novac Dev Team | 2 |  | Yes | TBD | TBD |  | 0%
3 | Data Migration | [6 empty] | 12 Weeks
3.1 | Legacy Data Profiling, Mapping & Clean-up | Analyze SystemaTIC database schema, map fields to STATIM, identify and perform data cleansing requirements. | Task | High | To Do | Santam Team | 15 |  | Yes | TBD | TBD |  | 0% |  | Poor data quality | Santam executes pre-migration clean | Mapping Doc
3.2 | Prod Data Extract | Client to provide production data extract | Task | Critical | To Do | Santam Team | 5 |  | Yes | TBD | TBD |  | 0%
3.3 | ETL Script Development | Write extraction, transformation, and load scripts for active policies, historical claims, and broker networks. | Task | Critical | To Do | Novac Migration Team | 20 |  | Yes | TBD | TBD |  | 0% | Prod Data Extract | Logic failures | Peer review ETL scripts
3.4 | Mock Migration 1 | Execute initial full data load into Dev. Validate record counts, financial balances, and referential integrity. | Task | Critical | To Do | Novac Migration Team | 5 |  | Yes | TBD | TBD |  | 0% |  | High error fallout | Tune ETL scripts iteratively
3.5 | Mock Migration 2 | Second pass migration using cleansed data for formal QA and UAT baseline data setup. | Task | High | To Do | Novac Migration Team | 5 |  | Yes | TBD | TBD |  | 0% |  | Extended execution time | Optimize indexing and bulk inserts |  |  | Sets stage for QA
3.6 | Mock 2 Validation | Business review of migrated data for accuracy | Task | Critical | To Do | Santam Team | 5 |  | Yes | TBD | TBD |  | 0%
3.7 | Data Migration Sign-off | Client to provide sign-off for the migrated data | Milestone | Critical | To Do | Santam Team | 1 |  | Yes | TBD | TBD |  | 0%
4 | Quality Assurance | [6 empty] | 8 Weeks
4.1 | SIT Test Case Preparation |  | Task | High | To Do | Novac QA Team | 8 |  | No | TBD | TBD |  | 0%
4.2 | Product, Rules & workflows configuration - Specific for Regression execution |  | Task | High | To Do | Novac QA Team | 8 |  | No | TBD | TBD |  | 0%
4.3 | SIT Execution | End-to-end execution of test cases across core PAS, portals, and all enterprise integrations (D365, Payment, etc.). | Task | Critical | To Do | Novac QA | 15 |  | Yes | TBD | TBD |  | 0%
4.4 | SIT Bug Fixes | Fix defects arising from QA environment execution | Task | High | To Do | Novac QA Team | 8 |  | Yes | TBD | TBD |  | 0%
4.5 | SIT Bug Re-testing & Fixes | Verify fixes and re-open failures if necessary | Task | High | To Do | Novac QA Team | 5 |  | Yes | TBD | TBD |  | 0%
4.6 | SIT Closure | Conclude primary SIT phase | Task | High | To Do | Novac QA Team | 1 |  | Yes | TBD | TBD |  | 0%
4.7 | Regression Testing | Execute regression on impacted functionality | Task | High | To Do | Novac QA Team | 10 |  | Yes | TBD | TBD |  | 0%
4.8 | Regression Bug Fixes | Fix bugs identified during regression | Task | High | To Do | Novac QA Team | 5 |  | Yes | TBD | TBD |  | 0%
4.9 | Regression Bug Re-testing & Fixes | Validate regression fixes | Task | High | To Do | Novac QA Team | 3 |  | Yes | TBD | TBD |  | 0%
4.10 | Regression Closure | Conclude regression phase | Task | High | To Do | Novac QA Team | 1 |  | Yes | TBD | TBD |  | 0%
4.11 | Vulnerability & Penetration Testing (VAPT) | Third-party/Santam InfoSec executes dynamic application security testing (DAST) and network pen-testing. | Task | Critical | To Do | Novac & Santam Team | 8 |  | No | TBD | TBD |  | 0% |  |  |  | VAPT Report
4.12 | Performance & Load Testing | Simulate concurrent portal users and bulk batch processing (renewals/finance) to validate AWS auto-scaling. | Task | High | To Do | Novac Dev & QA Team | 8 |  | No | TBD | TBD |  | 0% |  |  |  | Performance Test Report
4.13 | QA Sign-off | Obtain formal QA sign-off confirming exit criteria met | Milestone | Critical | To Do | Novac QA Team | 1 |  | Yes | TBD | TBD |  | 0%
4.14 | Addressing Product Configuration gaps | Address any configuration gaps | Task | Medium | To Do | Novac Product Team | 5 |  | No | TBD | TBD |  | 0%
5 | User Acceptance Testing | [6 empty] | 8 Weeks
5.1 | UAT Test Plan & Test Case Creation | Select critical UAT scenarios focusing on business processes | Task | High | To Do | Santam Team | 5 |  | No | TBD | TBD |  | 0%
5.2 | UAT Environment Refresh | Push Regression passed code and Mock 2 data to UAT | Task | High | To Do | Santam Team | 3 |  | Yes | TBD | TBD |  | 0%
5.3 | UAT - Train the trainers | Conduct deep-dive sessions on Product Configurator, Rules Engine, and User Access Management for Santam Admins. | Task | Medium | To Do | Novac & Santam Team | 5 |  | No | TBD | TBD |  | 0%
5.4 | User Acceptance Testing (UAT) Execution | Santam business users execute real-world scenarios, testing usability, accuracy, and operational readiness. | Task | Critical | To Do | Santam Team | 20 |  | Yes | TBD | TBD |  | 0% |  | UAT tester unavailability | Pre-book UAT calendar in Inception | UAT Defect Log
5.5 | UAT Change / Enhancement Request (If applicable) | Log any scope changes discovered during UAT | Task | Medium | To Do | Santam Team | 5 |  | No | TBD | TBD |  | 0%
5.6 | UAT Defect Resolution | Resolve blocker defects logged by Business Users | Task | High | To Do | Novac Dev Team | 8 |  | Yes | TBD | TBD |  | 0%
5.7 | UAT Defect Re-Testing & CR / Enhancement Testing | Validate UAT fixes and new CRs | Task | High | To Do | Novac & Santam Team | 5 |  | Yes | TBD | TBD |  | 0%
5.8 | UAT Sign-off | Formal review of outstanding defects (must be zero Sev 1/Sev 2) | Milestone | Critical | To Do | Santam Team | 1 |  | Yes | TBD | TBD |  | 0%
6 | Go-Live Readiness | [6 empty] | 2 Weeks
6.1 | Production Environment Provisioning | Provision AWS EC2, RDS, S3, and setup CI/CD pipelines, configure production SSLs, IP whitelists, and production DR sync. | Task | Critical | To Do | Novac DevOps Team | 5 |  | Yes | TBD | TBD |  | 0% |  | Network routing blocks | Final run-through with Networks
6.2 | Cutover Planning & Runbook Finalization | Finalize minute-by-minute cutover sequence, communication plan, and fail-back strategy. | Task | High | To Do | Novac & Santam Team | 5 |  | Yes | TBD | TBD |  | 0% |  | Misaligned responsibilities | Walkthrough runbook with all teams
6.3 | Final Data Migration (Cutover Weekend) | Freeze SystemaTIC. Execute final Delta ETL load into STATIM Production. Reconcile final GL balances. | Task | Critical | To Do | Novac Migration Team | 2 |  | Yes | TBD | TBD |  | 0% |  | Delta load exceeds window | Pre-load historicals, only delta on weekend |  |  | Weekend Task
7 | Go-Live | [6 empty] | 1 Day
7.1 | Go / No-Go Decision | Final authorization for production launch (Configurations & Data) | Task | Critical | To Do | Steering Committee | 1 |  | Yes | TBD | TBD |  | 0%
7.2 | Go-Live | Execute minimal impact live transactions to verify integrations. Switch DNS. Formally declare Go-Live. | Milestone | Critical | To Do | Novac & Santam Team | 1 |  | Yes | TBD | TBD |  | 0% |  | Smoke test failure | Execute rollback to SystemaTIC | Live System
8 | Post Go-Live | [6 empty] | 4 Weeks
8.1 | Hypercare Support (L2 & L3) | Immediate triage and ongoing support | Task | Critical | To Do | Novac Support Team | 20 |  | Yes | TBD | TBD |  | 0% |  | High query volume | Santam L1 to heavily filter queries
8.2 | BAU Transition & Project Closure | Formal sign-off transitioning platform into standard Application Maintenance and Support (AMS) SLA. | Milestone | High | To Do | Novac & Santam Team | 1 |  | Yes | TBD | TBD |  | 0% |  | Unresolved minor defects | Migrate to BAU backlog
[6 empty] | ID | Duration (Days) | Phase Duration | Critical Path
[6 empty] | 1 |  | 8 Weeks
[6 empty] | 1.1 | 1 |  | Yes
[6 empty] | 1.2 | 10 |  | Yes
[6 empty] | 1.3 | 8 |  | No
[6 empty] | 1.4 | 8 |  | Yes
[6 empty] | 1.5 | 8 |  | Yes
[6 empty] | 1.6 | 4 |  | No
[6 empty] | 1.7 | 1 |  | Yes
[6 empty] | 2 |  | 12 Weeks
[6 empty] | 2.1 | 10 |  | Yes
[6 empty] | 2.2 | 30 |  | Yes
[6 empty] | 2.3 | 15 |  | No
[6 empty] | 2.4 | 30 |  | Yes
[6 empty] | 2.5 | 2 |  | Yes
[6 empty] | 2.6 | 20 |  | Yes
[6 empty] | 2.7 | 20 |  | Yes
[6 empty] | 2.8 | 15 |  | No
[6 empty] | 2.9 | 12 |  | No
[6 empty] | 2.1 | 12 |  | No
[6 empty] | 2.11 | 2 |  | Yes
[6 empty] | 3 |  | 12 Weeks
[6 empty] | 3.1 | 15 |  | Yes
[6 empty] | 3.2 | 5 |  | Yes
[6 empty] | 3.3 | 20 |  | Yes
[6 empty] | 3.4 | 5 |  | Yes
[6 empty] | 3.5 | 5 |  | Yes
[6 empty] | 3.6 | 5 |  | Yes
[6 empty] | 3.7 | 1 |  | Yes
[6 empty] | 4 |  | 8 Weeks
[6 empty] | 4.1 | 8 |  | No
[6 empty] | 4.2 | 8 |  | No
[6 empty] | 4.3 | 15 |  | Yes
[6 empty] | 4.4 | 8 |  | Yes
[6 empty] | 4.5 | 5 |  | Yes
[6 empty] | 4.6 | 1 |  | Yes
[6 empty] | 4.7 | 10 |  | Yes
[6 empty] | 4.8 | 5 |  | Yes
[6 empty] | 4.9 | 3 |  | Yes
[6 empty] | 4.1 | 1 |  | Yes
[6 empty] | 4.11 | 8 |  | No
[6 empty] | 4.12 | 8 |  | No
[6 empty] | 4.13 | 1 |  | Yes
[6 empty] | 4.14 | 5 |  | No
[6 empty] | 5 |  | 8 Weeks
[6 empty] | 5.1 | 5 |  | No
[6 empty] | 5.2 | 3 |  | Yes
[6 empty] | 5.3 | 5 |  | No
[6 empty] | 5.4 | 20 |  | Yes
[6 empty] | 5.5 | 5 |  | No
[6 empty] | 5.6 | 8 |  | Yes
[6 empty] | 5.7 | 5 |  | Yes
[6 empty] | 5.8 | 1 |  | Yes
[6 empty] | 6 |  | 2 Weeks
[6 empty] | 6.1 | 5 |  | Yes
[6 empty] | 6.2 | 5 |  | Yes
[6 empty] | 6.3 | 2 |  | Yes
[6 empty] | 7 |  | 1 Day
[6 empty] | 7.1 | 1 |  | Yes
[6 empty] | 7.2 | 1 |  | Yes
[6 empty] | 8 |  | 4 Weeks
[6 empty] | 8.1 | 20 |  | Yes
[6 empty] | 8.2 | 1 |  | Yes

## Timeline
Phase / Month (Full Solution) | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7
Discovery & Planning
Implementation
Data Migration
Quality Assurance
User Acceptance Testing
Go-Live Readiness
Go-Live
Post Go-Live
Milestone Schedule
Milestone | Depends On | Target Date | Sign-off Owner | Status
Project Kick-off | - |  | Steering Committee
Phase 1 Sign-off | Discovery Complete |  | Santam Product
Core PAS Demo | Sprint Complete |  | Business Owner
Code Freeze | All Development Complete |  | Novac PM
Data Migration Sign-off | Mock Migration 2 |  | Santam IT
SIT Complete | Defects Closed |  | QA Lead
UAT Complete | SIT Closure |  | Santam Business
Go Live | Deployment Approval |  | Steering Committee
Hypercare Complete | 2-week stabilization |  | Joint

## RACI
Phase | Activity | Novac Steering Committee | Novac PMO Team | Novac Product Team | Novac Dev Team | Novac QA Team | Santam Steering Committee | Santam PMO Team | Santam Product Team | Santam Business Owner | Santam IT/Data Admin
Discovery & Planning | Project Kick-off | I | R | C | I | I | A | R | C | I | I
| Functional Discovery | I | A | R | C | I | A | I | R | C | C
| Technical & Arch Discovery | I | A | C | R | I | I | I | I | I | A, C
| Phase 1 Sign-off Gate | I | A | I | I | I | A | R | C | C | C
Implementation | Environment Provisioning | I | A | I | R | I | I | I | I | I | C
| Core Platform Configuration | I | A | R | R | I | I | I | C | C | I
| Enterprise Integrations | I | A | C | R | I | I | I | I | I | A, C
| Code Freeze & Review | I | A | I | R | C | I | I | I | I | I
Data Migration | SystemaTIC Data Clean-up | I | I | I | I | I | I | I | C | A | R
| ETL Scripts Development | I | A | I | R | I | I | I | I | I | C
| Mock Migration Executions | I | A | I | R | C | I | I | I | I | C
| Migration Data Validation | I | A | C | I | C | I | I | R | A,R | C
Quality Assurance | SIT Execution | I | A | C | I | R | I | I | I | I | I
| Defect Fixing (SIT) | I | A | C | R | C | I | I | I | I | I
| VAPT (Security Testing) | I | I | I | C | I | I | I | I | I | A, R
| QA Sign-off | I | A | I | I | R | I | I | I | I | I
User Acceptance Testing | UAT Environment Setup | I | A | I | R | I | I | A | I | I | R
| UAT Test Case Creation | I | I | C | C | C | I | A | R | C | I
| UAT Execution | I | I | C | I | C | I | I | R | A, R | I
| UAT Defect Triage | I | A | C | C | R | I | I | R | A | I
| UAT Defect Resolution | I | A | C | R | R | I | I | C | C | C
| UAT Sign-off | I | I | I | I | I | A | R | C | A, R | I
Go-Live | Legacy System Freeze | I | I | I | I | I | A | I | I | I | R
| Final Prod Data Cutover | I | A | I | R | I | I | I | I | I | C
| Go / No-Go Decision | A,R | C | C | C | C | A,R | C | C | C | C
| Go-Live | I | A | C | R | C | I | I | C | C | R
Post Go-Live | Hypercare Support (L2 & L3) | I | A | C | R | C | I | I | C | C | C
| BAU Transition & Project Closure | A | R | R | I | I | A | R | C | R | C
Key
R = Responsible | C = Consulted
A = Accountable | I = Informed

## Dependency Register
Dependency Register
ID | Activity | Depends On | Dependency Type | Owner | Risk | Proposed Mitigation
D01 | Project Kick-off | Project Initiation | External | Novac & Santam PMO | Medium | Confirm governance structure, project team and communication plan before kick-off.
D02 | Functional Discovery | Project Kick-off | Finish-to-Start | Novac Product Team | High | Ensure business SMEs are available for workshops and requirement discussions.
D03 | Technical & Architecture Discovery | Functional Discovery | Finish-to-Start | Novac Dev Team | High | Finalize integration specifications and infrastructure requirements early.
D04 | Phase 1 Sign-off | Functional & Technical Discovery Complete | Finish-to-Start | Novac PMO & Santam Steering Committee | High | Complete all reviews and obtain formal approval before implementation.
D05 | Core Platform Configuration & Integrations | Phase 1 Sign-off | Finish-to-Start | Novac Product & Dev Team | Critical | Freeze approved requirements and ensure external systems are available.
D06 | Data Migration Activities | Core Platform Configuration | Start-to-Start | Novac Migration Team & Santam IT | High | Complete data mapping, cleansing and production data extract before migration execution.
D07 | System Integration Testing (SIT) | Development, Integrations & Mock Migration Complete | Finish-to-Start | Novac QA Team | Critical | Deploy a stable build and migrated test data before SIT begins.
D08 | User Acceptance Testing (UAT) | QA Sign-off | Finish-to-Start | Santam Business Team | Critical | Refresh the UAT environment and complete business user readiness activities.
D09 | Production Cutover & Go-Live | UAT Sign-off | Finish-to-Start | Novac PMO & Santam PMO | Critical | Complete production readiness review, final migration and Go / No-Go approval.
D10 | Hypercare & Project Closure | Successful Go-Live | Finish-to-Start | Novac Support Team & Santam PMO | Medium | Monitor production stability, resolve priority issues and complete BAU transition.

## Critical Path
OVERVIEW The Critical Path represents the sequence of interdependent activities that directly determine the overall project duration and planned Go-Live. Activities on this path have no scheduling flexibility; delays to any critical activity or governance approval may impact the overall implementation timeline. The Critical Path has been derived from the indicative implementation schedule, dependency mapping, governance checkpoints, and the agreed RACI matrix.
CRITICAL PATH DIAGRAM | Step | Phase | Critical Activity | Primary Dependency | Novac Owner | Santam Owner | Governance Checkpoint
Project Kick-off | 1 | Discovery & Planning | Project Kick-off | Project Initiation | Novac PMO | Santam PMO | Project Kick-off
│ | 2 | Discovery & Planning | Functional Discovery | Project Kick-off | Novac Product Team | Santam Product Team | Discovery Workshops
▼ | 3 | Discovery & Planning | Technical & Architecture Discovery | Functional Discovery | Novac Dev Team | Santam IT / Data Admin | Technical Review
Functional Discovery | 4 | Discovery & Planning | Phase 1 Sign-off Gate | Functional & Technical Discovery Complete | Novac PMO | Santam Steering Committee | Phase Gate 1
│ | 5 | Implementation | Dev & QA Environment Provisioning | Phase 1 Sign-off | Novac Dev Team | Santam IT / Data Admin | Environment Readiness
▼ | 6 | Implementation | Core Platform Configuration | Environment Provisioning | Novac Product & Dev Team | Santam Product Team | Sprint Reviews
Technical & Architecture Discovery | 7 | Implementation | Enterprise Integrations | Core Platform Configuration | Novac Dev Team | Santam IT / Data Admin | Integration Readiness
│ | 8 | Implementation | Code Freeze & Integration Review | Development & Integrations Complete | Novac Dev Team | Santam PMO | Build Approval
▼ | 9 | Data Migration | ETL Script Development | Data Mapping & Production Extract | Novac Dev Team | Santam IT / Data Admin | ETL Readiness
Phase 1 Sign-off Gate | 10 | Data Migration | Mock Migration Execution | ETL Development Complete | Novac Dev Team | Santam IT / Data Admin | Migration Review
│ | 11 | Data Migration | Migration Data Validation | Mock Migration Complete | Novac Product Team | Santam Business Owner | Data Validation
▼ | 12 | Data Migration | Data Migration Sign-off | Migration Validation Complete | Novac PMO | Santam Business Owner | Phase Gate 2
Development & QA Environment Provisioning | 13 | Quality Assurance | System Integration Testing (SIT) | Migration Sign-off | Novac QA Team | Santam PMO | SIT Entry
│ | 14 | Quality Assurance | Defect Resolution & Regression Testing | SIT Execution | Novac Dev & QA Team | Santam Product Team | Regression Exit
▼ | 15 | Quality Assurance | QA Sign-off | Regression Complete | Novac QA Team | Santam PMO | Phase Gate 3
Core Platform Configuration | 16 | User Acceptance Testing | UAT Environment Setup | QA Sign-off | Novac Dev Team | Santam PMO | UAT Readiness
│ | 17 | User Acceptance Testing | User Acceptance Testing | UAT Environment Ready | Novac QA Team | Santam Business Owner | Business Validation
▼ | 18 | User Acceptance Testing | UAT Sign-off | UAT Complete | Novac PMO | Santam Steering Committee | Phase Gate 4
Enterprise Integrations | 19 | Go-Live Readiness | Production Environment Provisioning & Final Data Cutover | UAT Sign-off | Novac Dev Team | Santam IT / Data Admin | Production Readiness
│ | 20 | Go-Live | Go / No-Go Decision | Production Readiness Complete | Novac Steering Committee | Santam Steering Committee | Go / No-Go Meeting
▼ | 21 | Go-Live | Go-Live | Go / No-Go Approval | Novac Dev Team | Santam Business Owner | Production Release
Code Freeze & Integration Review | 22 | Post Go-Live | Hypercare Support | Successful Go-Live | Novac Support Team | Santam PMO | Hypercare Reviews
│ | 23 | Post Go-Live | BAU Transition & Project Closure | Hypercare Complete | Novac PMO | Santam PMO | Project Closure
▼
ETL Script Development
│
▼
Mock Migration Execution
│
▼
Migration Data Validation
│
▼
Data Migration Sign-off
│
▼
System Integration Testing (SIT)
│
▼
Defect Resolution & Regression Testing
│
▼
QA Sign-off
│
▼
UAT Environment Setup
│
▼
User Acceptance Testing
│
▼
UAT Sign-off
│
▼
Production Environment Provisioning
│
▼
Final Production Data Cutover
│
▼
Go / No-Go Decision
│
▼
Go-Live
│
▼
Hypercare Support
│
▼
BAU Transition & Project Closure

## Governance Calendar
Governance Calendar
Governance Activity | Frequency | Timeline | Participants | Chair / Owner | Purpose | Key Deliverables
Project Kick-off Meeting | Once | Project Initiation | Novac & Santam Project Teams | Novac PMO & Santam PMO | Formally initiate the project, confirm governance structure, roles, communication plan, and implementation approach. | Approved Project Charter, RACI Matrix, Communication Plan
Daily Stand-up | Daily (Mon–Fri) | Months 2–6 | Novac Delivery Team, Santam PMO (as required) | Novac PMO | Review daily progress, blockers, dependencies, and immediate priorities. | Action Items, Blocker Log
Weekly Project Status Meeting | Weekly | Months 1–7 | Novac PMO, Santam PMO, Functional & Technical Leads | Novac PMO | Review schedule, risks, issues, dependencies, deliverables, and upcoming activities. | Weekly Status Report, RAID Log Updates
Functional / Design Workshops | As Required | Months 1–2 | Product Teams, Business SMEs, Architects | Novac Product Team | Validate business requirements, product configuration, workflows, and solution design decisions. | Approved Functional Decisions, Design Updates
Technical Design Review | Weekly (During Design & Build) | Months 2–4 | Novac Dev Team, Santam IT/Data Admin | Novac Dev Team | Review solution architecture, integrations, infrastructure, security, and technical risks. | Architecture Decisions, Technical Action Log
Data Migration Review | Fortnightly | Months 4–6 | Migration Team, Santam IT/Data Admin, Business Representatives | Novac Migration Lead | Review migration progress, mapping, data quality, and validation outcomes. | Migration Status, Validation Reports
QA & Defect Review | Weekly | Months 3–5 | QA Team, Development Team, PMOs | Novac QA Lead | Review SIT, Regression progress, defect trends, and release readiness. | Defect Dashboard, QA Status Report
UAT Progress Review | Weekly | Months 5–6 | Santam Business Team, Novac PMO, QA Lead | Santam PMO | Monitor UAT execution, business feedback, defect resolution, and sign-off readiness. | UAT Progress Report, Open Issues Register
Go-Live Readiness Review | Weekly (Final Month) | Month 6 | Steering Committee, PMOs, Technical Leads | Joint PMO | Assess production readiness, cutover planning, deployment risks, and operational preparedness. | Go-Live Readiness Checklist
Go / No-Go Meeting | Once | Prior to Go-Live | Steering Committee, PMOs, Delivery Leads | Joint Steering Committee | Review final readiness criteria and approve production deployment. | Go / No-Go Decision Record
Hypercare Review Meeting | Weekly | Month 7 | Support Team, PMOs, Business Representatives | Novac PMO | Review production issues, stabilization progress, and transition readiness. | Hypercare Status Report
Project Closure Meeting | Once | End of Month 7 | Steering Committee, PMOs, Delivery Leads | Joint Steering Committee | Confirm completion of project objectives, transition to BAU, and formally close the project. | Project Closure Report, BAU Handover Sign-off
Governamce Checkpoints (Stage Gates)
Stage Gate | Trigger
Phase Gate 1 | Discovery & Planning Sign-off
Phase Gate 2 | Data Migration Sign-off
Phase Gate 3 | QA Sign-off
Phase Gate 4 | UAT Sign-off
Go / No-Go Gate | Production Readiness Approval
Project Closure Gate | BAU Transition & Hypercare Completion